## Project Schedule
Task ID | Task Name | Predecessor | Start Date | End Date | Duration (Days) | Assigned To | Status | Notes
T-001 | Site Preparation & Marking |  | 01-Aug-2026 | 07-Aug-2026 | 7 | Site Manager | Not Started
T-002 | Foundation Excavation | T-001 | 08-Aug-2026 | 18-Aug-2026 | 11 | Site Manager | Not Started
T-003 | PCC & RCC Foundation | T-002 | 19-Aug-2026 | 28-Aug-2026 | 10 | Site Manager | Not Started | 7 days curing
T-004 | Plinth Beam | T-003 | 29-Aug-2026 | 05-Sep-2026 | 8 | Site Manager | Not Started
T-005 | Ground Floor Columns | T-004 | 06-Sep-2026 | 15-Sep-2026 | 10 | Site Manager | Not Started
T-006 | Ground Floor Slab | T-005 | 16-Sep-2026 | 26-Sep-2026 | 11 | Site Manager | Not Started
T-007 | Ground Floor Brickwork | T-006 | 27-Sep-2026 | 10-Oct-2026 | 14 | Site Manager | Not Started
T-008 | First Floor Columns | T-006 | 27-Sep-2026 | 06-Oct-2026 | 10 | Site Manager | Not Started
T-009 | First Floor Slab | T-008 | 07-Oct-2026 | 17-Oct-2026 | 11 | Site Manager | Not Started
T-010 | Plastering (Internal) | T-007 | 11-Oct-2026 | 01-Nov-2026 | 22 | Site Manager | Not Started
T-011 | Electrical Rough-in | T-007 | 11-Oct-2026 | 25-Oct-2026 | 15 | Site Manager | Not Started
T-012 | Plumbing Rough-in | T-007 | 11-Oct-2026 | 25-Oct-2026 | 15 | Site Manager | Not Started
T-013 | Flooring | T-010 | 02-Nov-2026 | 20-Nov-2026 | 19 | Site Manager | Not Started
T-014 | Painting | T-013 | 21-Nov-2026 | 05-Dec-2026 | 15 | Site Manager | Not Started
T-015 | Handover | T-014 | 06-Dec-2026 | 10-Dec-2026 | 5 | PMC Head | Not Started