## Fee Schedule
Milestone No. | Milestone Description | % of Total Fee | Fee Amount (Rs.) | Due On | Notes
1 | Appointment & Agreement signing | 10 | 285000 | On agreement
2 | Submission of Design Drawings (Preliminary) | 10 | 285000 | Week 4
3 | Building Plan Sanction | 10 | 285000 | On sanction | Govt fees separate
4 | Good for Construction Drawings issued | 10 | 285000 | Week 10
5 | Foundation completion | 10 | 285000 | Per site progress
6 | Ground Floor slab completion | 10 | 285000 | Per site progress
7 | First Floor slab completion | 10 | 285000 | Per site progress
8 | Plastering completion | 10 | 285000 | Per site progress
9 | Finishing & Handover preparation | 10 | 285000 | Per site progress
10 | Practical Completion & Handover | 10 | 285000 | On handover
| TOTAL | 100%