## Project Schedule
Task ID | Task Name | Predecessor | Start Date | End Date | Duration (Days) | Assigned To | Status | Notes
T-001 | Site Preparation & Marking |  | 01-Aug-2026 | 07-Aug-2026 | 7 | Site Manager | Not Started
T-002 | Foundation Excavation | T-001 | 08-Aug-2026 | 18-Aug-2026 | 11 | Site Manager | Not Started
T-003 | Foundation Concrete (PCC + RCC) | T-002 | 19-Aug-2026 | 28-Aug-2026 | 10 | Site Manager | Not Started | 7 days curing
T-004 | Plinth Beam | T-003 | 29-Aug-2026 | 05-Sep-2026 | 8 | Site Manager | Not Started
T-005 | Ground Floor Columns | T-004 | 06-Sep-2026 | 15-Sep-2026 | 10 | Site Manager | Not Started
T-006 | Ground Floor Slab | T-005 | 16-Sep-2026 | 26-Sep-2026 | 11 | Site Manager | Not Started