## Claims
Claims — how we bill the client
A claim is raised once measurements are client-accepted. Three sign-offs (PMC + stream + principal) before approval. Invoice number recorded last.
The journey, at a glance:
Draft → PMC signed → Stream signed → Approved → Invoiced
Step-by-step
Step | Right now, it is: | Technical state | Who acts next | What they do | Moves to: | Change this?
Step 1 | Just created, no sign-offs yet | draft | PMC Head or Principal | Reviews draft claim and signs off | PMC has signed
Step 2 | PMC has signed | pmc_signed | Design Head or Services Head | Stream head reviews and signs | Stream has signed
Step 3 | Both PMC and stream have signed | stream_signed | Principal | Principal gives final approval | Approved
Step 4 | Approved, ready to invoice | approved | PMC Head or Principal | Records invoice number — claim becomes a live invoice | Invoiced

## Measurements
Measurements — recording work done on site
Quantities of work physically completed. Stream head signs, then client formally accepts. Client acceptance unlocks claim raising.
The journey, at a glance:
Draft → Stream signed → Client accepted
Step-by-step
Step | Right now, it is: | Technical state | Who acts next | What they do | Moves to: | Change this?
Step 1 | Just recorded on site | draft | Design Head or Services Head | Stream head reviews and signs | Stream signed
Step 2 | Stream head has signed | rs_signed | PMC Head or Principal | Records client formal acceptance — signed certificate uploaded | Client accepted

## Snags
Snags — defects spotted on site
A snag is a defect that needs fixing. Open → vendor rectifies → senior verifies and closes.
The journey, at a glance:
Open → Rectified → Closed
Step-by-step
Step | Right now, it is: | Technical state | Who acts next | What they do | Moves to: | Change this?
Step 1 | Just raised, defect reported | open | Site Mgr, Sr Site Mgr, PMC Head or Principal | Marks snag rectified once vendor has fixed it | Rectified
Step 2 | Vendor has claimed it's fixed | rectified | PMC Head, Design Head, Services Head or Principal | Verifies fix on site and closes snag | Closed
Exceptions / alternate paths
| If currently in: | Technical state | Who can act | What they do | Result | Change this?
⚠ | open | open | PMC Head, Design Head, Services Head or Principal | Minor snags closed directly without rectified step | closed

## Weekly Reports
Weekly Reports — sent to client every week
Three sections (PMC, Design, Services). Each section head signs their section. When all three signed, Principal approves, then marks sent.
The journey, at a glance:
Draft → Pending review → Approved → Sent
Step-by-step
Step | Right now, it is: | Technical state | Who acts next | What they do | Moves to: | Change this?
Step 1 | Being written, sections unsigned | draft | PMC, Design, Services Heads | Each head signs their section. All three signed → moves automatically. | Pending review
Step 2 | All three sections signed | pending_review | Principal | Principal approves the report | Approved
Step 3 | Approved, ready to send | approved | Principal | Marks report as sent to client (timestamp + audit) | Sent

## Payment Requests
Payment Requests — paying vendors
Raised by site/PMC/heads → PMC review → auto-approve (below threshold) or Principal approval → payment released.
The journey, at a glance:
Pending PMC → PMC approved → Approved → Paid
Step-by-step
Step | Right now, it is: | Technical state | Who acts next | What they do | Moves to: | Change this?
Step 1 | Submitted by raiser | pending_pmc | PMC Head or Principal | PMC reviews and approves | PMC approved
Step 2 | PMC approved; system routes next | pmc_approved | System (automatic) | Below threshold → auto-approved. Above → goes to Principal. | Approved or Pending Principal
Step 3 | Waiting for Principal | pending_naveen | Principal | Principal approves or rejects | Approved or Rejected
Step 4 | Approved, ready to pay | approved | Finance Admin or Principal | Payment released; UTR recorded | Paid
Exceptions / alternate paths
| If currently in: | Technical state | Who can act | What they do | Result | Change this?
⚠ | pending_naveen | pending_naveen | Principal | Rejected — raiser and PMC reviewer both notified via WhatsApp | rejected
⚠ | approved | approved | Finance Admin | ICICI batch file processed — status moves to cleared then paid | cleared

## Issues
Issues — site problems being tracked
Any project member can raise. Moves through open → in_progress → resolved → closed. PMC or heads close.
The journey, at a glance:
Open → In progress → Resolved → Closed
Step-by-step
Step | Right now, it is: | Technical state | Who acts next | What they do | Moves to: | Change this?
Step 1 | Just raised | open | Assignee | Starts working on it | In progress
Step 2 | Being worked on | in_progress | Assignee | Marks it resolved | Resolved
Step 3 | Assignee says it's fixed | resolved | PMC Head, Design/Services Head or Principal | Verifies and closes | Closed
Exceptions / alternate paths
| If currently in: | Technical state | Who can act | What they do | Result | Change this?
⚠ | open | open | PMC Head, Design/Services Head or Principal | Direct close for minor issues | closed

## Change Notices
Change Notices — changes to scope / cost / schedule
Formal record of project change. Principal raises, stream heads sign, Principal approves. Has contractual weight.
The journey, at a glance:
Draft → Pending approval → Approved
Step-by-step
Step | Right now, it is: | Technical state | Who acts next | What they do | Moves to: | Change this?
Step 1 | Just drafted by Principal | draft | PMC, Design, Services Heads + Principal | Stream heads sign the change notice | Pending approval
Step 2 | Stream heads have signed | pending_approval | Principal | Principal approves | Approved
Exceptions / alternate paths
| If currently in: | Technical state | Who can act | What they do | Result | Change this?
⚠ | pending_approval | pending_approval | Principal | Principal rejects — change not recorded as approved | rejected

## Drawings
Drawings — design documents issued to site
Upload → L1 review (detailing/services head) → L2 approve & issue (design head/principal) → Issued. Superseded when new revision issued.
The journey, at a glance:
Uploaded → Under review → Issued
Step-by-step
Step | Right now, it is: | Technical state | Who acts next | What they do | Moves to: | Change this?
Step 1 | Just uploaded | uploaded | Design Head, Services Head or Principal | Starts review (L1 or direct to L2) | Under review
Step 2 | Being reviewed | under_review | Design Head, Services Head or Principal | Approves and issues to site | Issued
Exceptions / alternate paths
| If currently in: | Technical state | Who can act | What they do | Result | Change this?
⚠ | under_review | under_review | Design Head, Services Head or Principal | Revision required — sent back with comments | rejected
⚠ | issued | issued | Design Head or Principal | Newer revision issued — old one locked | superseded

## Submittals
Submittals — material samples / vendor product submissions
Vendor submits material sample. Design/services head reviews. Four outcomes: approved / approved with comments / resubmit / rejected.
The journey, at a glance:
Submitted → Under review → Approved
Step-by-step
Step | Right now, it is: | Technical state | Who acts next | What they do | Moves to: | Change this?
Step 1 | Submittal arrived | submitted | Design Head, Services Head or Principal | Starts reviewing | Under review
Step 2 | Being reviewed | under_review | Design Head, Services Head or Principal | Approves (clean or comments) | Approved
Exceptions / alternate paths
| If currently in: | Technical state | Who can act | What they do | Result | Change this?
⚠ | under_review | under_review | Design Head, Services Head or Principal | Revisions needed — vendor resubmits | resubmit_required
⚠ | under_review | under_review | Design Head, Services Head or Principal | Rejected outright | rejected
⚠ | resubmit_required | resubmit_required | Site Manager or Coordinator | Vendor resubmits revised submittal | submitted