## SLA Table
nu PMC — SLA & Escalation Table
SLA days verified from routes/project-slas.js DEFAULTS and routes/dashboard.js. Edit SLA days here.
Item Type | Description | SLA (days) | Escalation 1 | Escalation 2 | Notes | Source in Code | Change this?
GRN
GRN | GRN clearance — time from creation to approval | 2 | PMC Head | Principal | Day 1 reminder to PMC; Day 2 escalate to Principal | project-slas.js:27
Drawing
Drawing | Drawing approval — time from upload to L2 issue | 3 | Design Head | Principal | From upload timestamp. >3 days = RED in weekly health | project-slas.js:28, weekly-health.js:79
RFI
RFI | RFI response — time from raise to answer | 5 | Design Head / Services Head | Principal | Design or services depending on drawing stream | project-slas.js:29
Clearance
Clearance | Vendor clearance — time from vendor creation to clearance | 7 | Finance Admin | Principal | Finance admin must clear before any payment request | project-slas.js:30
MOM
MOM | MOM issue — time from approval to client receipt | 3 | PMC Head | Principal | From MOM approval timestamp | project-slas.js:31
PR
PR | Payment request — PMC review after raise | 2 | PMC Head | Principal | SLA on PMC review only, not full approval chain | project-slas.js:32
Drawing query
Drawing query | Drawing query (RFI in issue tracker) — response time | 3 | Design Head | Principal | Flagged RED in dashboard after 3 days (routes/dashboard.js:12) | dashboard.js:12,25
Weekly report
Weekly report | Weekly report sign-off — all 3 sections signed | 2 | PMC Head | Principal | From report draft creation timestamp | reports.js (implied)
Snag
Snag | Snag rectification — vendor fixes defect | 14 | Site Manager | PMC Head | Calendar days; vendor is responsible party | convention
User approval
User approval | New user pending — Principal approval | 1 | Principal | Design Principal | Same-day expectation — blocks user from logging in | user-management.js